## To-Do-List
Project Backlog
Task | Description | Due Date | Status
Finish setting up documentation files |  | 2013-07-10 | Completed
Create dummy data | For testing | 2013-07-10 | Not Started
Complete MiniProject 01 | The goal is to have the program recognize when the user types a known character’s name or setting from the data set. When the user wants to know the stats of the current draft, the program will show how often the characters and settings are used. | 2013-07-11 | Not Started
Complete MiniProject 02 | Create database schema that includes characters, locations, chapters and tasks. | 2013-07-12 | Not Started
Complete MiniProject 03 | The goal of this mini project is to make a working database that can hold the data used in mini-project one as well as the rest of the Blue Script site. | 2013-07-19 | Not Started
Refresh Yourself on CRUD | in ASP.NET MVC 3. This needs to be done ASAP | 2013-07-09 | Pending
Design Logo for BlueScript | Some type of blue feather pen | NA | Not Started