## To-Do-List
Project Backlog
Task | Description | Week | Status
Finish setting up documentation files | According to assignment shown online | 1 | Completed
Create dummy data | For testing | 4 | Completed
String counter | using regex, let user know how often a certain name comes up in their writing. (pre-miniproject 01) | 1 | Completed
Create Mockup for Home page | Hi-fi | 2 | Completed
Create Mockup for My Work page | Hi-fi | 2 | Completed
Create Mockup for Settings/Locations page | Hi-fi | 2 | Completed
Create Mockup for Characters page | Hi-fi | 2 | Completed
Create Mockup for Chapters page | Hi-fi | 2 | Completed
Create outline of why Front-end has technical depth | This document will show everything that goes into the front-end of a website | 2 | Completed
Refresh Yourself on CRUD | in ASP.NET MVC 3. This needs to be done ASAP | 1 | Completed
Design Logo for BlueScript | Some type of blue feather pen | 1 | Completed
Implement Security | Start simple |  | Not Started
Create Home page | The Welcome page, where you can login/sign up for Blue Script. |  | Pending
Create basic layout of BlueScript | By layout I mean the HTML shown on all pages on Blue Script based on mockups |  | Pending
Create My Blue Script Page | Mindmap page |  | Pending
Highlighting text using JavaScript |  | 2 | Completed
Clear current highlights when entering in new string to look for. |  |  | Not Started
implement drag and drop |  | 3 | Completed
look into books on writing to use their terms | Make all terms used in the website relatable to writers | 4 | Pending
Add Feature(Scenes) | Be able to add a new scene(Event) with the click of a button. The new scene will show up right as you click the button ready for the user to edit without leaving the current screen. | 4 | Pending
Delete Feature | The user will be able to delete a scene(Event) without deleting the locations(settings) and characters that are part of the scene. | 4 | Pending
Edit Feature | Be able to edit scenes(Events) without going to a new screen on the web site. | 4 | Pending
Add Feature(Characters/Settings) | Be able to add a new character and setting with the click of a button. A Modal(small popup) will show where you can add the details about the character/setting before saving it to the database. | 4 | Pending