## To-Do-List
Project Backlog
Task | Description | Week | Status
Finish setting up documentation files | According to assignment shown online | 1 | Completed
Create dummy data | For testing |  | Not Started
String counter | using regex, let user know how often a certain name comes up in their writing. (pre-miniproject 01) | 1 | Completed
Create Mockup for Home page | Hi-fi | 2 | Completed
Create Mockup for My Work page | Hi-fi | 2 | Completed
Create Mockup for Settings/Locations page | Hi-fi | 2 | Completed
Create Mockup for Characters page | Hi-fi | 2 | Completed
Create Mockup for Chapters page | Hi-fi | 2 | Completed
Create outline of why Front-end has technical depth | This document will show everything that goes into the front-end of a website | 2 | Completed
Create Entities | Includes: Characters, settings/locations, chapters |  | Not Started
Complete MiniProject 01 | The goal is to have the program recognize when the user types a known character’s name or setting from the data set. When the user wants to know the stats of the current draft, the program will show how often the characters and settings are used. |  | Not Started
Complete MiniProject 02 | Create database schema that includes characters, locations, chapters and tasks. |  | Not Started
Complete MiniProject 03 | The goal of this mini project is to make a working database that can hold the data used in mini-project one as well as the rest of the Blue Script site. |  | Not Started
Refresh Yourself on CRUD | in ASP.NET MVC 3. This needs to be done ASAP | 1 | Completed
Design Logo for BlueScript | Some type of blue feather pen | 1 | Completed
Remove code that seeds the database in BlueScript | Note When you deploy an application to a production web server, you must remove code that seeds the database. |  | Not Started
Implement Security | Start simple |  | Not Started
Create Home page | The Welcome page, where you can login/sign up for Blue Script. | 3 | Not Started
Create Characters page | This page shows a list of the current characters in the current project with basic information. An add new character button will be in plain view. |  | Not Started
Create Settings/Locations page |  |  | Not Started
Create basic layout of BlueScript | By layout I mean the HTML shown on all pages on Blue Script based on mockups | 3 | Not Started
Create Chapters page |  |  | Not Started
Create My Work page |  |  | Not Started
Create Add/Edit/Delete features | Includes: Characters, settings/locations, chapters |  | Not Started
Highlighting text using JavaScript |  | 2 | Completed
Clear current highlightswhen entering in new string to look for. |  | 3 | Not Started